## Checklist
Phase | Task | Done | Notes
Phase 1: Diagnosis & Segmentation (Days 1-7) | Data Access: Confirm read/write access to core behavioral and billing data stores. | FALSE
Phase 1: Diagnosis & Segmentation (Days 1-7) | Define Segmentation: Define 6-8 core segments (Plan/ARPA, ICP Tier, Acquisition Channel, etc.) for initial slicing. | FALSE
Phase 1: Diagnosis & Segmentation (Days 1-7) | Voluntary vs. Involuntary: Cleanse churn data and accurately label all lost accounts as Voluntary (explicit cancel) or Involuntary (payment failure). | FALSE
Phase 1: Diagnosis & Segmentation (Days 1-7) | Calculate Leak Rates: Calculate initial Gross Revenue Retention (GRR) and Net Revenue Retention (NRR) rates, segmented by acquisition cohort. | FALSE
Phase 2: Funnel Mapping & Hypotheses (Days 8-14) | Map The Value Funnel: Define the key steps from signup –1 first value –1 activation –1 weekly usage –1 adoption depth –1 renewal. | FALSE
Phase 2: Funnel Mapping & Hypotheses (Days 8-14) | Identify Drop-Off Cliffs: Pinpoint the funnel step with the highest drop-off percentage (e.g., "never reached first value" or "activated then decayed"). | FALSE
Phase 2: Funnel Mapping & Hypotheses (Days 8-14) | Root-Cause Hypotheses: Develop 5 testable root-cause hypotheses for the Top 5 leaky segments. | FALSE
Phase 2: Funnel Mapping & Hypotheses (Days 8-14) | Identify Persuadables: Use early data to identify the "movable middle" cohorts (high sensitivity to intervention). | FALSE
Phase 2: Funnel Mapping & Hypotheses (Days 8-14) | Action Plan: Assign owners (CSM, Product, Support) and response SLAs (Service Level Agreements) to the identified high-risk/persuadable cohorts. | FALSE