## 90-Day Retention Plan Checklist
90-Day Retention Transformation Plan – Checklist
Phase | Days | Task | Status
X-Ray & Ownership | 1–14 | Appoint a Retention Owner (single accountable person)
X-Ray & Ownership | 1–14 | Ship segmented GRR/NRR dashboard with voluntary/involuntary split
X-Ray & Ownership | 1–14 | Identify persuadable cohorts and outreach rules
X-Ray & Ownership | 1–14 | Start weekly Retain Board (Product, CS, Growth, Finance)
Foundations & Involuntary | 15–45 | Eliminate P0 bugs and reliability blockers (SLOs)
Foundations & Involuntary | 15–45 | Launch Dunning v1 (card updater, smart retries, localized comms, in-app banner)
Foundations & Involuntary | 15–45 | Send pre-expiry nudges for cards expiring soon
Foundations & Involuntary | 15–45 | Add a Pause option for short-term risk accounts
Voluntary v1 & Activation | 46–70 | Implement cancel flow v1 (reason capture → branching saves → clean exit)
Voluntary v1 & Activation | 46–70 | Redesign first-week activation (role-based checklist, contextual nudges, event-triggered comms)
Voluntary v1 & Activation | 46–70 | Map early user milestones ('first value', 'aha' moments)
Health & Expansion | 71–90 | Launch Health Score v1 with playbooks
Health & Expansion | 71–90 | Wire alerts to CSM queues and tasks
Health & Expansion | 71–90 | Launch first expansion motion (add-on or seat growth)
Health & Expansion | 71–90 | Run QBR-style internal review: what moved GRR/NRR; where to double-down